## Slide 1: Mapping the Missing Project Update
Nelson Foster
DATS 6501-10 | Data Science Capstone
2 July 2019

## Slide 2: Agenda
Revised Problem Statement
Current Progress
Challenges
Next Steps

## Slide 3: Refined Problem Statement
Law enforcement personnel and community organizations tend to lack comprehensive, consolidated, data-driven tools to address missing persons cases.
A consolidated, consistent and current database of spatiotemporal and demographic data on missing persons can help law enforcement and advocacy groups identify trends in missing persons data and potentially investigate incidences of exploitation such as human trafficking or serial crime.

## Slide 4: Current Progress
Project Planning/Research
  Literature Review on missing persons research and data-driven interventions
    Urban Indian Health Institute (Seattle Indian Health Board)
  Identified potential data sources
    NamUs
    National Center for Missing & Exploited Children
    Nine State/local law enforcement agencies
    Social Media (#missingperson)
  Researching web scraping technologies
    Beautiful Soup
    Selenium
    Requests
    Flask
  Consulting with Geospatial Statistics Professor on Spatial Analysis and Mapping techniques using R
  Updates to Trello Board & Linked GitHub Repo

## Slide 5: Challenges
Data Acquisition
  Deciding on data sources
  Existing “official” data sources are problematic
    Lack of standard data structure or governance method
    Incomplete or redacted/amended records
    Not updated timely
    Inconsistency in encoding and capture methods across jurisdictions
  After reviewing some implementations using DoJ’s website (NamUs), considering either supplementing or shifting focus from official data sources
  Deciding on web scraping method and learning how to implement it
  Constrained by what data source(s) are ultimately utilized
* “Official” in this context refers to databases compiled by federal, state, & local law enforcement agencies, as well as non profit organizations, NGOs, and advocacy groups

## Slide 6: Next Steps
Narrow down data source(s), scope/region(s) of research
Decide on web scraping framework
Design/build research environment in AWS
  Compute (EC2)
  Storage
    Documents/files (S3 buckets)
    Database (Amazon RDS)
Code data pipelines/APIs to acquire data and store in cloud RDS
Reconvene with Geospatial Statistics Professor
Develop spatial analyses, hypothesis tests, maps, etc.
Develop data product/deliverable
  Single-page web application
Refine data product/deliverable and prepare presentations

## Slide 7: Questions/Suggestions?